## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a customer-account executive /cashier / teller I want to be able to log in the bank website with my user ID and password So that I carry out my transactions | Task 1 | Anagha | Write a program for displaying the login page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the login page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 4 | Viren | Write test conditions to test the login page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 5 | Rohan | Write a program for validation of input provided by user | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 6 | Rohan | Write a program for user login | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 7 | Viren | Write test conditions to test login page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 8 | Satej | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
US002 | As a customer-account executive I want to be able to capture new customer information So that I can create a new customer in the system | Task 1 | Anagha | Write a program for displaying the create customer page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the create customer page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 4 | Satej | Write test conditions to test the create customer page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 5 | Rohan | Write a program for validation of input provided by user | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 6 | Rohan | Write a program to create new customer | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 7 | Viren | Write test conditions to test new customer page | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
|  | Task 8 | Rohan | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 0 | Closed
US003 | As a customer-account executive I want to be able to edit existing customer information So that I can store the updated customer information in the system | Task 1 | Anagha | Write a program for displaying the update customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the update customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 5 | Rohan | Write a program to check if customer record exists or not | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 6 | Rohan | Write a program to update existing customer | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 7 | Viren | Write test conditions to test update customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 8 | Satej | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
US004 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Anagha | Write a program for displaying the delete customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the delete customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 5 | Rohan | Write a program to check if customer record exists or not | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 6 | Rohan | Write a program to delete existing customer | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 7 | Viren | Write test conditions to test delete customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 8 | Satej | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
US004 | As a customer-account executive I want to be able to delete existing customer from system | Task 1 | Anagha | Write a program for displaying the delete customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the delete customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | Rohan | Write a program to check if customer record exists or not | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 6 | Rohan | Write a program to delete existing customer | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 7 | Viren | Write test conditions to test delete customer page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 8 | Satej | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
US005 | As a customer-account executive I want to be able to view the status of all the customers of the bank | Task 1 | Anagha | Write a program for displaying the customer status page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the customer status page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | Rohan | Write a program for displaying customer status | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | Viren | Write test conditions to test customer status page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 6 | Viren | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
US006 | As a customer-account executive I want to be able to capture account details So that I can create a new bank account for an existing customer | Task 1 | Anagha | Write a program for displaying the create account page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Anagha | Design the UI for the create account page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | Rohan | Write a program to check if customer record exists or not | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 6 | Rohan | Write a program to create new account for an existing customer | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 7 | Viren | Write test conditions to test create account page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 8 | Satej | Execute the tests | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
US007 | As a customer-account executive I want to be able to delete an account of an existing customer | Task 1 | Anagha | Write a program for displaying the delete account page | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 2 | Anagha | Design the UI for the delete account page | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 5 | Viren | Write a program to check if account exists or not | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 6 | Rohan | Write a program to display account details before deleting | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 7 | Rohan | Write a program to delete account of existing customer | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 8 | Viren | Write test conditions to test create account page | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 9 | Satej | Execute the tests | 2 | 2 | 2 | 2 | 0 |  |  | Closed
US008 | As a customer-account executive I want to be able to view the status of all the accounts of the bank | Task 1 | Anagha | Write a program for view account status page | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 2 | Anagha | Design the UI for the account status page | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 4 | Rohan | Write a program to view account status | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 5 | Viren | Write test conditions to test account status page | 2 | 2 | 2 | 2 | 0 |  |  | Closed
|  | Task 6 | Satej | Execute the tests | 2 | 2 | 2 | 2 | 0 |  |  | Closed
US009 | As a customer-account executive I want to be able to search for a customer So that I am able to view the details | Task 1 | Anagha | Write a program for customer search page | 1 | 1 | 1 | 1 | 0 |  |  | Closed
|  | Task 2 | Anagha | Design the UI for the customer search page | 1 | 1 | 1 | 1 | 0 |  |  | Closed
|  | Task 3 | Satej | Design and create the DB fields | 1 | 1 | 1 | 1 | 0 |  |  | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 1 | 1 | 1 | 1 | 0 |  |  | Closed
|  | Task 5 | Rohan | Write a program to search for a customer | 1 | 1 | 1 | 1 | 0 |  |  | Closed
|  | Task 6 | Viren | Write test conditions to test customer search page | 1 | 1 | 1 | 1 | 0 |  |  | Closed
|  | Task 7 | Satej | Execute the tests | 1 | 1 | 1 | 1 | 0 |  |  | Closed
US010 | As a Cashier/ Teller I want to be able to search for a bank account So that I am able to view the details | Task 1 | Anagha | Write a program for bank account search page | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 2 | Anagha | Design the UI for the bank account search page | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 3 | Satej | Design and create the DB fields | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 5 | Rohan | Write a program to search for a bank account | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 6 | Viren | Write test conditions to test bank account search page | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 7 | Satej | Execute the tests | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
US011 | As a Cashier/ Teller I want to be able to deposit money into a customer's account So that I am able to service the customer's request | Task 1 | Anagha | Write a program for deposit money page | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 2 | Anagha | Design the UI for the deposit money page | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 3 | Satej | Design and create the DB fields | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 5 | Viren | Write a program to search for a bank account | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 6 | Rohan | Write a program to deposit money in bank account | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 7 | Viren | Write test conditions to test deposit money page | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
|  | Task 8 | Satej | Execute the tests | 2 | 2 | 2 | 2 | 2 | 0 |  | Closed
US012 | As a Cashier/ Teller I want to be able to withdraw money from a customer's account So that I am able to service the customer's request | Task 1 | Anagha | Write a program for withdraw money page | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 2 | Anagha | Design the UI for the withdraw money page | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 3 | Satej | Design and create the DB fields | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 4 | Rohan | Write a program for validation of input provided by user | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 5 | Viren | Write a program to search for a bank account | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 6 | Rohan | Write a program to withdraw money from bank account | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 7 | Viren | Write test conditions to test withdraw money page | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
|  | Task 8 | Satej | Execute the tests | 1 | 1 | 1 | 1 | 1 | 0 |  | Closed
US013 | As a Cashier/ Teller I want to be able to transfer money from a customer's account So that I am able to service the customer's request | Task 1 | Anagha | Write a program for transfer money page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 2 | Anagha | Design the UI for the transfer money page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 4 | Rohan | Write a program for displaying customer details before initiating the transaction | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 5 | Rohan | Write a program to transfer money onr bank account to other | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 6 | Rohan | Write a program for displaying acount details after the transaction is completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 7 | Viren | Write test conditions to test withdraw money page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 8 | Viren | Execute the tests | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
US014 | As a Cashier/ Teller I want to be able to print an account statement So that I am able to service the customer's request | Task 1 | Anagha | Write a program for account statement page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 2 | Anagha | Design the UI for the account statement page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 3 | Satej | Design and create the DB fields | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 4 | Rohan | Write a program to display account statement online | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 5 | Viren | Write test conditions to test account statement page | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
|  | Task 6 | Viren | Execute the tests | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Closed
[5 empty] | 190 | 158 | 122 | 82 | 45 | 14 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
200 | 160 | 125 | 85 | 50 | 15 | 0
190 | 158 | 122 | 82 | 45 | 14 | 0